## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group 4
| Project | DoughDoughs Online Ordering System
| Product Owner | Emma Monroy- Rincon, Lindy Nguyen
| Scrum Master | Francesca Nazzal
| Development Team | Antoine Gaton and Wesley McElhinny
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Website Setup & Menu | View restaurant's menu with descriptions, images, and prices. | Menu items are displayed with descriptions, prices, and images. Menu is accessible on both mobile and desktop devices. | High | 1 | Dev Team
2 | User Authentication System | Implement the authentication system for user registration | Have Next-Auth implemented for authentication and have a successful logon. | High | 1 | Dev Team
3 | Admin Dashboard | Create a back-end dashboard for administrators | Dashboard appears with only administrative items when logged in under an admin | High | 1 | Dev Team
4 | Additional pages | Create additional pages for information about the company | Have a filled out menu page, about us page, contact page, order confirmation page, user profile page and checkout flow page | Medium | 1 | Dev Team
5 | Database Integration | Integrate the backend database with the website | Successful checkout of a pizza and updated admin page based on sales | Medium | 2 | Dev Team
6 | Testing | The system will undergo regression testing against it | System does not break and functionality works as intended | Medium | 2 | Dev Team
7 | Documentation | Documentation is created for the client to utilize the website | Completed package is delivered | Low | 1 & 2 | Product Owner
8 | Confirmation email Template | Create a template for confirmation email of order | Have a completed template ready to be sent out to customer | Low | 1 & 2 | Product Owner
| Customer Presentation | Customer introduction | Setup and organize customer introduction to product | Low | 1 | Product Owner

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2024-11-19
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02
1 | 1 | Set up Next.js 13 framework | Antoine Gaton | 2 | 2024-11-19: 2
2 | 1 | Set up sdhadcn/ui component library | Antoine Gaton | 1 | bar: 2024-11-19
3 | 1 | Configure Tailwind CSS with custom theme | Antoine Gaton | 1 | bar: 2024-11-20
4 | 1 | Establish project structure and organization | Antoine Gaton | 1 | bar: 2024-11-20
5 |  | Implement responsive navigation bar | Antoine Gaton | 2 | 2024-11-19: 2
6 | 1 | Create hero section with video background | Wesley McElhinny | 2 | 2024-11-21: 2
7 | 1 | Build feature showcase with hover effects | Wesley McElhinny | 2 | 2024-11-21: 2
8 | 1 | Add popular pizzas gallery with dynamic loading | Antoine Gaton | 2 | 2024-11-21: 2
9 | 1 | Implement custom order scheme | Antoine Gaton | 2 | 2024-11-22: 2
10 | 1 | Set up responsive breakpoints | Antoine Gaton | 2 | 2024-11-23: 2
11 | 1 | Establish component styling patters | Wesley McElhinny | 1 | bar: 2024-11-20
12 | 1 | Create Consistent typography system | Wesley McElhinny | 1 | bar: 2024-11-20
1 | 2 | Create login page with form validation | Antoine Gaton | 2
2 | 2 | Create Registration Flow with email verification | Antoine Gaton | 2
3 | 2 | Password reset functionality | Antoine Gaton | 2
4 | 2 | Protected routes implementation | Antoine Gaton | 2
1 | 3 | Create Order management interface | Antoine Gaton | 3
2 | 3 | Implement product inventory control | Antoine Gaton | 2
3 | 3 | Implement user mangement system | Antoine Gaton | 3
4 | 3 | Create sales analytics overview | Antoine Gaton | 2
1 | 4 | Create Menu page with filtering options | Wesley McElhinny | 1
2 | 4 | Create About us page | Wesley McElhinny | 1
3 | 4 | Create/fill Contacts page | Wesley McElhinny | 1
4 | 4 | Create/fill Oder confirmation page | Wesley McElhinny | 1
5 | 4 | Create user checkout page | Wesley McElhinny | 1
6 | 4 | Create checkout flow page | Wesley McElhinny | 1
1 | 8 | Create customer confirmation email. | Product Owner | 1
1 | 7 | Create documentation for the basic user guide for the product | Product Owner/dev team | 8
|  | Remaining units (actual) |  | 64 | 59 | 55 | 49 | 47 | 45 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2024-12-10
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23
1 | 5 | Connect order menu to database | Antoine Gaton | 2
2 | 5 | Connect login page to database | Antoine Gaton | 2
1 | 6 | Test forms for input validation | Wes McElhinny | 2
2 | 6 | Test page loading on multiple devices | Emma Monroy- Rincon | 1
3 | 6 | Test functional use of ordering | Lindy Nguyen | 1
4 | 6 | Test page navigation | Francesca Nazzal | 1
2 | 7 | Finalize documentation for the basic user guide for the product | Emma Monroy- Rincon, Lindy Nguyen | 3
1 | 9 | Organize and conduct a meeting to review sprint 2 and the final product. | Emma Monroy- Rincon, Lindy Nguyen | 4
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 16 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0