## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group D
| Project | DoughDoughs Online Ordering System
| Product Owner | Emma Monroy- Rincon
| Scrum Master | Michael McCory
| Development Team | Antoine Gaton and Wesley McElhinny
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Website Setup & Menu | View restaurant's menu with descriptions, images, and prices. | Menu items are displayed with descriptions, prices, and images. Menu is accessible on both mobile and desktop devices. | High | 1 | Dev Team
2 | Ordering System | Place a customized order for pizza and other menu items. | Customers can select menu items, customize orders, and save them with confirmation. | High | 1 | Dev Team
3 | Billing System | Calculate and display the final price, including discounts. | Total price is calculated based on item selection and customization. Discounts and promotions are applied. | High | 1 | Dev Team
4 | Payment and Processing | Pay for an order securely using credit cards. | Secure payment gateway integrated. Customers can pay with valid credit card information. | High | 1 | Dev Team
5 | Order Confirmation & Tracking | Pay for an order securely using credit cards. | Order confirmation is received and customers can track the order status. | Medium | 2 | Dev Team
6 | Menu Management for Store Managers | Add, update, or remove menu items, prices, and promotions. | Managers can securely update menu items, prices, and promotions in real-time. | Medium | 2 | Dev Team
7 | User Authentication and Registration | Register and log in to save order history and favorites. | Users can register, log in, and access their order history and favorite orders. | Low | 2 | Dev Team
8 | Admin Panel for Sales Monitoring | Monitor and view sales reports for the pizzeria. | Admin panel displays detailed reports of sales and order history. | Low | 2 | Dev Team
9 | Technical Support / Infrastructure | Set up the essential infrastructure and support systems needed to enable development, testing, and deployment of the pizza ordering system. | The project repository and necessary environments are fully configured and accessible to the team. Sprint planning, review meetings, and basic testing are conducted and documented, ensuring development can proceed smoothly and securely | High | 1 & 2 | Dev Team

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2024-10-19
|  |  | Total Team Members | 2
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01
1 | 1 | Set up basic web framework and initial database configuration | Antoine Gaton | 1
2 | 1 | Create responsive menu page design with sample data | Wesley McElhinny | 1.5
3 | 1 | Backend API to fetch menu items and connect database | Antoine Gaton | 1
4 | 1 | Integrate images, descriptions, prices in UI | Wesley McElhinny | 1
5 | 1 | Basic testing and bug fixes | Antoine Gaton | 0.5
1 | 2 | Implement simple customizable order flow (select item and add to cart) | Antoine Gaton | 2
2 | 2 | UI for customization options (toppings, size) | Wesley McElhinny | 1
3 | 2 | Save order in session and display order summary | Antoine Gaton | 1
4 | 2 | Testing for order placement | Antoine Gaton | 0.5
1 | 3 | Calculate and display order total | Antoine Gaton | 1
2 | 3 | Apply simple discounts and promotions (hard-coded for MVP) | Wesley McElhinny | 0.5
3 | 3 | Backend logic for total calculation | Antoine Gaton | 0.5
4 | 3 | Testing | Wesley McElhinny | 0.5
1 | 4 | Set up basic payment gateway (Stripe sandbox) | Antoine Gaton | 1
2 | 4 | Simple secure payment form (collect credit card info) | Wesley McElhinny | 1
3 | 4 | Process payments and return status | Antoine Gaton | 1
4 | 4 | Testing | Wesley McElhinny | 0.5
1 | 9 | Sprint 2 planning and backlog refinement | Antoine Gaton | 0.5
2 | 9 | Performance testing for ordering and billing systems | Antoine Gaton | 1
3 | 9 | Sprint 2 review, demo preparation, and client feedback | Wesley McElhinny | 0.5
|  | Remaining units (actual) |  | 32 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 1.0658e-14
[10 empty] | 0 | 17.5 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2024-12-10
|  |  | Total Team Members | 2
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23
1 | 5 | Implement confirmation screen | Wesley McElhinny | 1
2 | 5 | Simple order tracking backend logic (hard-coded statuses) | Antoine Gaton | 1
3 | 5 | Integrate frontend with tracking API | Wesley McElhinny | 1
4 | 5 | Testing | Antoine Gaton | 0.5
1 | 6 | Build simple UI for adding/removing menu items | Wesley McElhinny | 1.5
2 | 6 | Backend logic for updating menu items | Antoine Gaton | 1
3 | 6 | Permissions for store manager | Antoine Gaton | 0.5
4 | 6 | Testing | Antoine Gaton | 0.5
1 | 7 | Set up user registration and login | Antoine Gaton | 1
2 | 7 | Basic session management and password encryption | Antoine Gaton | 1
3 | 7 | Testing | Wesley McElhinny | 0.5
1 | 8 | Simple UI for sales report | Wesley McElhinny | 1.5
2 | 8 | Backend logic for pulling report data | Antoine Gaton | 1
3 | 8 | Testing | Antoine Gaton | 0.5
1 | 9 | Sprint 2 planning and backlog refinement | Antoine Gaton | 0.5
2 | 9 | Performance testing for ordering and billing systems | Wesley McElhinny | 1
3 | 9 | Sprint 2 review, demo preparation, and client feedback | Antoine Gaton | 0.5
|  | Remaining units (actual) |  | 32 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 1.0658e-14
[10 empty] | 0 | 14.5 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0