## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group 1
| Project | DoughDoughs Online Ordering System
| Product Owner | Emma Monroy- Rincon
| Scrum Master | Michael McCory
| Development Team | Antoine Gaton and Wesley McElhinny
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Website Setup & Menu | View restaurant's menu with descriptions, images, and prices. | Menu items are displayed with descriptions, prices, and images. Menu is accessible on both mobile and desktop devices. | High | 1 | Dev Team
2 | Ordering System | Place a customized order for pizza and other menu items. | Customers can select menu items, customize orders, and save them with confirmation. | High | 1 | Dev Team
3 | Billing System | Calculate and display the final price, including discounts. | Total price is calculated based on item selection and customization. Discounts and promotions are applied. | High | 1 | Dev Team
4 | Payment and Processing | Pay for an order securely using credit cards. | Secure payment gateway integrated. Customers can pay with valid credit card information. | High | 1 | Dev Team
5 | Order Confirmation & Tracking | Pay for an order securely using credit cards. | Order confirmation is received and customers can track the order status. | Medium | 2 | Dev Team
6 | Menu Management for Store Managers | Add, update, or remove menu items, prices, and promotions. | Managers can securely update menu items, prices, and promotions in real-time. | Medium | 2 | Dev Team
7 | User Authentication and Registration | Register and log in to save order history and favorites. | Users can register, log in, and access their order history and favorite orders. | Low | 2 | Dev Team
8 | Admin Panel for Sales Monitoring | Monitor and view sales reports for the pizzeria. | Admin panel displays detailed reports of sales and order history. | Low | 2 | Dev Team

## Sprint 1
Sprint #Tracking Sheet
Project
Sprint #
Start date
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #Tracking Sheet
Project
Sprint #
Start date
Total Team Members
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Remaining units (actual) |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0